## All Projects
New South Wales Projects
Project Details - Eurobodalla Southern Storage Announced - 2021 Funding Allocated - $51.2 million
Project Stage | Commencement Date | Completion Date
1. Community and stakeholder engagement | 2018 | 2018
2. Final Business case | 2018 | 2021
3. Planning and Pre-Construction Activities | 2021 | Early 2022
4. Construction (incl. procurement and main construction) | Early 2022 | Late 2024
Project Details - Dungowan Pipeline - Stage 1 Announced - 2016 Funding Allocated - $80.0 million
Project Stage | Commencement Date | Completion Date
1. Community and stakeholder engagement | 2020-10-01 | 2022-12-01
2. Final Business case | 2019 | 2022-08-01
3. Planning and Pre-Construction Activities | 2020-10-01 | N/A
4. Construction (incl. procurement and main construction) | 2022-02-01 | Mid-2023
Project Details - Nyngan to Cobar Pipeline - Stage 1 Announced - 2022 Funding Allocated - $22.75 million
Project Stage | Commencement Date | Completion Date
1. Community and stakeholder engagement | 2020 | 2024
2. Final Business case | 2020 | Mid-2022
3. Planning and Pre-Construction Activities | 2022 | 2024
4. Construction (incl. procurement and main construction) | Mid-2024 | Late 2026
Project Details - Wyangala Dam Wall Raising Announced - 2019 Funding Allocated - $325 million (construction funding deferred)
Project Stage | Commencement Date | Completion Date
1. Community and stakeholder engagement | Early 2020 | Mid-2023
2. Final Business case | Early 2020 | Mid-2023
3. Planning and Pre-Construction Activities | Mid-2022 | Mid-2023
4. Construction (incl. procurement and main construction) | TBC | TBC
Victoria Projects
Project Details - East Grampians Water Supply Project Announced - 2019 Funding Allocated - $32.0 million (TBD)
Project Stage | Commencement Date | Completion Date
1. Community and stakeholder engagement | 2018 | 2024
2. Final Business case | 2018 | 2019
3. Planning and Pre-Construction Activities | 2019 | Mid-2020
4. Construction (incl. procurement and main construction) | Late 2023 | Early 2026
Project Details - Macalister Irrigation District (MID) Modernisation Phase 2 Announced - 2019 Funding Allocated - $31.3 million
Project Stage | Commencement Date | Completion Date
1. Community and stakeholder engagement | 2021 | 2021
2. Final Business case | 2018 | 2018
3. Planning and Pre-Construction Activities | 2018 | Mid 2022
4. Construction (incl. procurement and main construction) | Mid-2021 | Late 2024
Project Details - Quality Water for Wannon Announced - 2023 Funding Allocated - $26.1 million
Project Stage | Commencement Date | Completion Date
1. Community and stakeholder engagement | TBC | TBC
2. Final Business case | TBC | TBC
3. Planning and Pre-Construction Activities | Mid-2023 | Late 2028
4. Construction (incl. procurement and main construction) | Late 2023 | 2029
Project Details - Recycled Water on the Bellarine Announced - 2021 Funding Allocated - $5.5 million
Project Stage | Commencement Date | Completion Date
1. Community and stakeholder engagement | 2021 | 2024
2. Final Business case | N/A | Complete
3. Planning and Pre-Construction Activities | 2021 | Mid-2023
4. Construction (incl. procurement and main construction) | Late 2023 | Mid-2025
Project Details - Western Irrigation Network Announced - 2020 Funding Allocated - $48.1 million
Project Stage | Commencement Date | Completion Date
1. Community and stakeholder engagement | 2018 | 2025
2. Final Business case | 2018 | 2019
3. Planning and Pre-Construction Activities | 2019 | Mid-2020
4. Construction (incl. procurement and main construction) | Late 2020 | Mid-2025
Project Details - Werribee Irrigation District Modernisation Phase 4 & 5 Announced - 2021 Funding Allocated - $10.9 million
Project Stage | Commencement Date | Completion Date
1. Community and stakeholder engagement | 2021 | 2021
2. Final Business case | Complete | Complete
3. Planning and Pre-Construction Activities | 2021 | Early 2023
4. Construction (incl. procurement and main construction) | Mid-2023 | Mid-2025
Completed Projects | Funding Provided | Completion Date
1. Macalister Irrigation District Modernisation Phase 1B | $20.0 million | 2020-11-01
2. Mitiamo and District Reticulated Water Supply Project | $14.5 million | 2021
3. South West Loddon Rural Water Supply Project | $20.0 million | 2020
4. Sunraysia Modernisation Project 2 | $3.0 million | 2019-10-01
Queensland Projects
Project Details - Big Rocks Weir Announced - 2018 Funding Allocated - $38.0 million
Project Stage | Commencement Date | Completion Date
1. Community and stakeholder engagement | 2018 | TBD
2. Final Business case | 2018 | 2020
3. Planning and Pre-Construction Activities | 2021 | Late 2023
4. Construction (incl. procurement and main construction) | TBD | TBD
Project Details - Cairns Water Security Program - Stage 1 Announced - 2022 Funding Allocated - $107.5 million
Project Stage | Commencement Date | Completion Date
1. Community and stakeholder engagement | 2021 | 2026
2. Final Business case | 2021 | Late 2022
3. Planning and Pre-Construction Activities | 2021 | 2024
4. Construction (incl. procurement and main construction) | TBD | TBD
Project Details - Mount Morgan Water Supply Announced - 2022 Funding Allocated - $3.5 million
Project Stage | Commencement Date | Completion Date
1. Community and stakeholder engagement | 2021 | 2024
2. Final Business case | 2021 | Mid-2022
3. Planning and Pre-Construction Activities | Early 2022 | Late 2023
4. Construction (incl. procurement and main construction) | TBD | TBD
Project Details - Paradise Dam Improvement Announced - 2022 Funding Allocated - $600.0 million
Project Stage | Commencement Date | Completion Date
1. Community and stakeholder engagement | 2019 | TBD
2. Final Business case | 2019 | 2024
3. Planning and Pre-Construction Activities | 2020 | TBD
4. Construction (incl. procurement and main construction) | Late 2023 | TBD
Project Details - Rookwood Weir Announced - 2018 Funding Allocated - $183.6 million
Project Stage | Commencement Date | Completion Date
1. Community and stakeholder engagement | 2018 | Late 2023
2. Final Business case | 2016 | Late 2017
3. Planning and Pre-Construction Activities | 2018 | Mid-2021
4. Construction (incl. procurement and main construction) | 2020 | Late 2023
Project Details - Warwick Recycled Water Treatment Upgrade Announced - 2021 Funding Allocated - $0.5 million
Project Stage | Commencement Date | Completion Date
1. Community and stakeholder engagement | N/A | N/A
2. Final Business case | 2020 | 2021
3. Planning and Pre-Construction Activities | 2020 | Late 2022
4. Construction (incl. procurement and main construction) | Late 2022 | Late 2023
Project Details - Hughenden Irrigation Scheme Announced - 2018 Funding Allocated - $170.0 million (construction funding deferred)
Project Stage | Commencement Date | Completion Date
1. Community and stakeholder engagement | 2018 | TBD
2. Final Business case | 2018 | Mid-2022
3. Planning and Pre-Construction Activities | 2021 | TBD
4. Construction (incl. procurement and main construction) | TBD | TBD
Completed Projects | Funding Provided | Completion Date
1. Mareeba-Dimbulah Water Supply Scheme | $11.6 million | 2021
Tasmania Projects
Project Details - Bicheno Recycled Water Scheme Announced - 2022 Funding Allocated - $5.0 million
Project Stage | Commencement Date | Completion Date
1. Community and stakeholder engagement | Late 2022 | Late 2023
2. Final Business case | 2021 | Mid-2023
3. Planning and Pre-Construction Activities | 2022 | Mid-2023
4. Construction (incl. procurement and main construction) | Late 2023 | Late 2024
Project Details - Don Irrigation Scheme Announced - 2019 Funding Allocated - $26.3 million
Project Stage | Commencement Date | Completion Date
1. Community and stakeholder engagement | 2018 | 2023
2. Final Business case | 2020 | Early 2022
3. Planning and Pre-Construction Activities | 2020 | Early 2022
4. Construction (incl. procurement and main construction) | 2022 | Late 2023
Project Details - Lake Leake Dam Life Extension Upgrade Announced - 2022 Funding Allocated - $1.5 million
Project Stage | Commencement Date | Completion Date
1. Community and stakeholder engagement | 2022 | Mid 2023
2. Final Business case | 2022 | 2022
3. Planning and Pre-Construction Activities | Early 2022 | Mid-2022
4. Construction (incl. procurement and main construction) | Early 2023 | Mid-2023
Project Details - Northern Midlands Irrigation Scheme Announced - 2019 Funding Allocated - $109.0 million
Project Stage | Commencement Date | Completion Date
1. Community and stakeholder engagement | 2018 | 2024
2. Final Business case | 2020 | Late 2022
3. Planning and Pre-Construction Activities | 2020 | Mid 2023
4. Construction (incl. procurement and main construction) | Mid-2023 | Late 2025
Project Details - Sassafras-Wesley Vale Irrigation Scheme Announced - 2019 Funding Allocated - $62.1 million
Project Stage | Commencement Date | Completion Date
1. Community and stakeholder engagement | 2018 | Late 2023
2. Final Business case | 2020 | Late 2022
3. Planning and Pre-Construction Activities | Late 2023 | Early 2024
4. Construction (incl. procurement and main construction) | Mid-2024 | Late 2026
Project Details - Tamar Irrigation Scheme Announced - 2019 Funding Allocated - $16.4 million
Project Stage | Commencement Date | Completion Date
1. Community and stakeholder engagement | 2019 | 2025
2. Final Business case | 2020 | Late 2023
3. Planning and Pre-Construction Activities | 2020 | TBD
4. Construction (incl. procurement and main construction) | TBD | TBD
Completed Projects | Funding Provided | Completion Date
1. Scottsdale Irrigation Scheme | $25.3 million | Late 2020
South Australia Projects
Project Details - Northern Adelaide Irrigation Scheme Announced - 2017 Funding Allocated - $45.6 million
Project Stage | Commencement Date | Completion Date
1. Community and stakeholder engagement | 2018 | TBD
2. Final Business case | N/A | N/A
3. Planning and Pre-Construction Activities | 2018 | 2019
4. Construction (incl. procurement and main construction) | 2018 | TBD
Northern Territory Projects
Project Details - Darwin Region Water Supply Infrastructure Program - Stage 1 Announced - 2022 Funding Allocated - $300.6 million
Project Stage - Manton Dam Return to Service | Commencement Date | Completion Date
1. Community and stakeholder engagement | N/A | N/A
2. Final Business case | 2018 | 2021
3. Planning and Pre-Construction Activities | 2018 | 2025
4. Construction (incl. procurement and main construction) | 2024 | 2026
Project Stage - Adelaide River Off-stream Water Storage Pre-Construction | Commencement Date | Completion Date
1. Community and stakeholder engagement | Early 2022 | 2024
2. Final Business case | 2018 | Late 2021
3. Planning and Pre-Construction Activities | Early 2022 | Late 2024
4. Construction (incl. procurement and main construction) | TBD | TBD
*Note there are no projects currently underway in the Australian Capital Territory.

## NSW
New South Wales Projects
Project Details - Eurobodalla Southern Storage Announced - 2021 Funding Allocated - $51.2 million
Project Stage | Commencement Date | Completion Date
1. Community and stakeholder engagement | 2018 | 2018
2. Final Business case | 2018 | 2021
3. Planning and Pre-Construction Activities | 2021 | Early 2022
4. Construction (incl. procurement and main construction) | Early 2022 | Late 2024
Project Details - Dungowan Pipeline- Stage 1 Announced - 2016 Funding Allocated - $80.0 million
Project Stage | Commencement Date | Completion Date
1. Community and stakeholder engagement | 2020-10-01 | 2022-12-01
2. Final Business case | 2019 | 2022-08-01
3. Planning and Pre-Construction Activities | 2020-10-01 | N/A
4. Construction (incl. procurement and main construction) | 2022-02-01 | Mid 2023
Project Details - Nyngan to Cobar Pipeline - Stage 1 Announced - 2022 Funding Allocated - $22.75 million
Project Stage | Commencement Date | Completion Date
1. Community and stakeholder engagement | 2020 | 2024
2. Final Business case | 2020 | Mid 2022
3. Planning and Pre-Construction Activities | 2022 | 2024
4. Construction (incl. procurement and main construction) | Mid 2024 | Late 2026
Project Details - Wyangala Dam Wall Raising Announced - 2019 Funding Allocated - $325 million (construction funding deferred)
Project Stage | Commencement Date | Completion Date
1. Community and stakeholder engagement | Early 2020 | Mid 2023
2. Final Business case | Early 2020 | Mid 2023
3. Planning and Pre-Construction Activities | Mid 2022 | Mid 2023
4. Construction (incl. procurement and main construction) | TBC | TBC

## VIC
Victoria Projects
Project Details - East Grampians Water Supply Project Announced - 2019 Funding Allocated - $32.0 million (TBD)
Project Stage | Commencement Date | Completion Date
1. Community and stakeholder engagement | 2018 | 2024
2. Final Business case | 2018 | 2019
3. Planning and Pre-Construction Activities | 2019 | Mid 2020
4. Construction (incl. procurement and main construction) | Late 2023 | Early 2026
Project Details - Macalister Irrigation District (MID) Modernisation Phase 2 Announced - 2019 Funding Allocated - $31.3 million
Project Stage | Commencement Date | Completion Date
1. Community and stakeholder engagement | 2021 | 2021
2. Final Business case | 2018 | 2018
3. Planning and Pre-Construction Activities | 2018 | Mid 2022
4. Construction (incl. procurement and main construction) | Mid 2021 | Late 2024
Project Details - Quality Water for Wannon Announced - 2023 Funding Allocated - $26.1 million
Project Stage | Commencement Date | Completion Date
1. Community and stakeholder engagement | Mid 2023 | 2029
2. Final Business case | 2019 | 2022
3. Planning and Pre-Construction Activities | Mid 2023 | Late 2028
4. Construction (incl. procurement and main construction) | 2024-2025 | 2029
Project Details - Recycled Water on the Bellarine Announced - 2021 Funding Allocated - $5.5 million
Project Stage | Commencement Date | Completion Date
1. Community and stakeholder engagement | 2021 | 2024
2. Final Business case | N/A | Complete
3. Planning and Pre-Construction Activities | 2021 | Mid 2023
4. Construction (incl. procurement and main construction) | Late 2023 | Mid 2025
Project Details - Western Irrigation Network Announced - 2020 Funding Allocated - $48.1 million
Project Stage | Commencement Date | Completion Date
1. Community and stakeholder engagement | 2018 | 2025
2. Final Business case | 2018 | 2019
3. Planning and Pre-Construction Activities | 2019 | Mid 2020
4. Construction (incl. procurement and main construction) | Late 2020 | Mid 2025
Project Details - Werribee Irrigation District Modernisation Phase 4 & 5 Announced - 2021 Funding Allocated - $10.9 million
Project Stage | Commencement Date | Completion Date
1. Community and stakeholder engagement | 2021 | 2021
2. Final Business case | Complete | Complete
3. Planning and Pre-Construction Activities | 2021 | Early 2023
4. Construction (incl. procurement and main construction) | Mid 2023 | Mid 2025
Completed Projects | Funding Provided | Completion Date
1. Macalister Irrigation District Modernisation Phase 1B | $20.0 million | 2020-11-01
2. Mitiamo and District Reticulated Water Supply Project | $14.5 million | 2021
3. South West Loddon Rural Water Supply Project | $20.0 million | 2020
4. Sunraysia Modernisation Project 2 | $3.0 million | 2019-10-01
*

## QLD
Queensland Projects
Project Details - Big Rocks Weir Announced - 2018 Funding Allocated - $38.0 million
Project Stage | Commencement Date | Completion Date
1. Community and stakeholder engagement | 2018 | TBD
2. Final Business case | 2018 | 2020
3. Planning and Pre-Construction Activities | 2021 | Late 2023
4. Construction (incl. procurement and main construction) | TBD | TBD
Project Details - Cairns Water Security Program - Stage 1 Announced - 2022 Funding Allocated - $107.5 million
Project Stage | Commencement Date | Completion Date
1. Community and stakeholder engagement | 2021 | 2026
2. Final Business case | 2021 | Late 2022
3. Planning and Pre-Construction Activities | 2021 | 2024
4. Construction (incl. procurement and main construction) | TBD | TBD
Project Details - Mount Morgan Water Supply Announced - 2022 Funding Allocated - $3.5 million
Project Stage | Commencement Date | Completion Date
1. Community and stakeholder engagement | 2021 | 2024
2. Final Business case | 2021 | Mid 2022
3. Planning and Pre-Construction Activities | Early 2022 | Late 2023
4. Construction (incl. procurement and main construction) | TBD | TBD
Project Details - Paradise Dam Improvement Announced - 2022 Funding Allocated - $600.0 million
Project Stage | Commencement Date | Completion Date
1. Community and stakeholder engagement | 2019 | TBD
2. Final Business case | 2019 | 2024
3. Planning and Pre-Construction Activities | 2020 | TBD
4. Construction (incl. procurement and main construction) | Late 2023 | TBD
Project Details - Rookwood Weir Announced - 2018 Funding Allocated - $183.6 million
Project Stage | Commencement Date | Completion Date
1. Community and stakeholder engagement | 2018 | Late 2023
2. Final Business case | 2016 | Late 2017
3. Planning and Pre-Construction Activities | 2018 | Mid 2021
4. Construction (incl. procurement and main construction) | 2020 | Late 2023
Project Details - Warwick Recycled Water Treatment Upgrade Announced - 2021 Funding Allocated - $0.5 million
Project Stage | Commencement Date | Completion Date
1. Community and stakeholder engagement | N/A | N/A
2. Final Business case | 2020 | 2021
3. Planning and Pre-Construction Activities | 2020 | Late 2022
4. Construction (incl. procurement and main construction) | Late 2022 | Late 2023
Project Details - Hughenden Irrigation Scheme Announced - 2018 Funding Allocated - $170.0 million (construction funding deferred)
Project Stage | Commencement Date | Completion Date
1. Community and stakeholder engagement | 2018 | TBD
2. Final Business case | 2018 | Mid 2022
3. Planning and Pre-Construction Activities | 2021 | TBD
4. Construction (incl. procurement and main construction) | TBD | TBD
Completed Projects | Funding Provided | Completion Date
1. Mareeba-Dimbulah Water Supply Scheme | 11.6 million | 2021

## TAS
Tasmania Projects
Project Details - Bicheno Recycled Water Scheme Announced - 2022 Funding Allocated - $5.0 million
Project Stage | Commencement Date | Completion Date
1. Community and stakeholder engagement | Late 2022 | Late 2023
2. Final Business case | 2021 | Mid 2023
3. Planning and Pre-Construction Activities | 2022 | Mid 2023
4. Construction (incl. procurement and main construction) | Late 2023 | Late 2024
Project Details - Don Irrigation Scheme Announced - 2019 Funding Allocated - $26.3 million
Project Stage | Commencement Date | Completion Date
1. Community and stakeholder engagement | 2018 | 2023
2. Final Business case | 2020 | Early 2022
3. Planning and Pre-Construction Activities | 2020 | Early 2022
4. Construction (incl. procurement and main construction) | 2022 | Late 2023
Project Details - Lake Leake Dam Life Extension Upgrade Announced - 2022 Funding Allocated - $1.5 million
Project Stage | Commencement Date | Completion Date
1. Community and stakeholder engagement | 2022 | Mid 2023
2. Final Business case | 2022 | 2022
3. Planning and Pre-Construction Activities | Early 2022 | Mid 2022
4. Construction (incl. procurement and main construction) | Early 2023 | Mid 2023
Project Details - Northern Midlands Irrigation Scheme Announced - 2019 Funding Allocated - $109.0 million
Project Stage | Commencement Date | Completion Date
1. Community and stakeholder engagement | 2018 | 2024
2. Final Business case | 2020 | Late 2022
3. Planning and Pre-Construction Activities | 2020 | Mid 2023
4. Construction (incl. procurement and main construction) | Mid 2023 | Late 2025
Project Details - Sassafras-Wesley Vale Irrigation Scheme Announced - 2019 Funding Allocated - $31.0 million
Project Stage | Commencement Date | Completion Date
1. Community and stakeholder engagement | 2018 | Late 2023
2. Final Business case | 2020 | Late 2022
3. Planning and Pre-Construction Activities | Late 2023 | Early 2024
4. Construction (incl. procurement and main construction) | Mid 2024 | Late 2026
Project Details - Tamar Irrigation Scheme Announced - 2019 Funding Allocated - $12.5 million
Project Stage | Commencement Date | Completion Date
1. Community and stakeholder engagement | 2019 | 2025
2. Final Business case | 2020 | Late 2023
3. Planning and Pre-Construction Activities | 2020 | TBD
4. Construction (incl. procurement and main construction) | TBD | TBD
Completed Projects | Funding Provided | Completion Date
1. Scottsdale Irrigation Scheme | $25.3 million | Late 2020

## SA
South Australia Projects
Project Details - Northern Adelaide Irrigation Scheme Announced - 2017 Funding Allocated - $45.6 million
Project Stage | Commencement Date | Completion Date
1. Community and stakeholder engagement | 2018 | TBD
2. Final Business case | N/A | N/A
3. Planning and Pre-Construction Activities | 2018 | 2019
4. Construction (incl. procurement and main construction) | 2018 | TBD

## NT
Northern Territory Projects
Project Details - Darwin Region Water Supply Infrastructure Program - Stage 1 Announced - 2022 Funding Allocated - $300.6 million
Project Stage - Manton Dam Return to Service | Commencement Date | Completion Date
1. Community and stakeholder engagement | N/A | N/A
2. Final Business case | 2018 | 2021
3. Planning and Pre-Construction Activities | 2018 | 2025
4. Construction (incl. procurement and main construction) | 2024 | 2026
Project Stage - Adelaide River Off-stream Water Storage Pre Construction | Commencement Date | Completion Date
1. Community and stakeholder engagement | Early 2022 | 2024
2. Final Business case | 2018 | Late 2021
3. Planning and Pre-Construction Activities | Early 2022 | Late 2024
4. Construction (incl. procurement and main construction) | TBD | TBD